## Sheet1
CEREMONIES | DEFINITION | ATTENDESS | LENGTH | FREQUENCY | COMMENTS
DAILY SCRUM | What we did yesterday, what we did today, mention blockers Morning meeting 11AM Avoid to resolve issues in the scrum Find a room/ space to join for scrum. Stand up preferred. Repurpose time as long as blockers are highlighted/ also for demos/ Retrospective | ALL | 15MINS | Daily - Except Tuesday
PLANNING | Prep-what's coming - next Goal for the sprint-Objective Assess past velocity Story readiness Identify capacity from the team Pulls and commit | PO, Team, SM | 30 - 60 MINS | One-Time
GROOMING | Breaking stories down How many stories go into the sprint (mindful) Responsibilities assigned Rank and prioritized Entering stories into backlog? <TBD | PO, Team, SM | 30MINS | 1-2 Times x Sprint | Discussion btwn Derek and Todd in reaching an agreement on how the requirements from Confluence can be reflected in JIRA backlog. |  | - 1-2 before sprint ends
WORKING SESSIONS | Estimates provided Details Creating stories Define 'HOW', lengtn Define technical and design approach | PO (when needed), Team | 1HR | 2 - 3 x week |  | - 1hr mx
BACKLOG SESSIONS | N/A < Grooming
REVIEW / DEMO | No localhost/ deploy in DEV PO accepting the 'Done' of deliverables for this sprint PO sign-off Occurs at the end of the sprint Move on | PO, Team, SM | 30MINS | 1 middle of the Sprint 1 End of the Sprint
RETROSPECTIVE | Did well/ improve React on opportunities for improvement Lessons learned | ALL | 30MINS | One-Time
Recommendations> | Start meeting on time/ define agenda
DEFINITIONS
Ready | MUST HAVE: Clear definition-requirements Title Identify dependency(es) Acceptance criteria (scenarios) NICE TO HAVE: Mocks (n/a to enhancements or fixes) Data mapping Documentation related to story
Done | PO final signoff Accept QA guidance Automate test scripts x story Pass unit testing E2E whole integration of the component on each page Moved to 'Resolve' status in JIRA workflow